## Information
Para Equestrian Toolkit
Event Checklist
1 | Event Details | Complete with information about event
2 | Event checklist | Planning checklist for pre- and post-event
3 | Venue facilities | Checklist for what faciilties are available at event
This spreadsheet has been put together to assist clubs and organising committees with planning a para dressage event. It is a guide only and can be modified to suit the needs of an individual event.

## 1. Event Details
Event Details
Organiser
Event Name
Event Location
Event Start Date
Event End Date
Event Organiser Resources | https://www.equestrian.org.au/event-organisers
Organisers Guide (generic)
Volunteer Register | https://volunteersignup.org/
Sanctioning and Approvals
Rules | https://www.equestrian.org.au/rules

## 2. Event Planning Checklist
ORGANISER | 0 |  |  | KEY PERSONNEL | ROLE |  | NAME | EMAIL | PHONE | ACCREDITED
EVENT START DATE | 0 |  |  | #1 |  |  | <insert name> | <insert email> | <insert number> | 1
LOCATION | 0 |  |  | #2 |  |  | <insert name> | <insert email> | <insert number> | 1
|  |  |  | #3 |  |  | <insert name> | <insert email> | <insert number> | 1
Event Manager |  |  |  | #4 |  |  | <insert name> | <insert email> | <insert number> | 0
NAME | EMAIL ADDRESS |  | CONTACT NUMBER | #5 |  |  | <insert name> | <insert email> | <insert number> | 0
|  |  |  | #6 |  |  | <insert name> | <insert email> | <insert number> | 0
|  |  |  | #7 |  |  | <insert name> | <insert email> | <insert number> | 0
|  |  |  | #8 |  |  | <insert name> | <insert email> | <insert number> | 0
|  |  |  | #9 |  |  | <insert name> | <insert email> | <insert number> | 0
|  |  |  | #10 |  |  | <insert name> | <insert email> | <insert number> | 0
For above, enter -1 = cross, 0 = exclaimation mark, 1 = tick
| ITEM | ORGANISATION RESPONSIBLE | PERSON RESPONSIBLE | WEEKS PRIOR | DEADLINE | STATUS | NOTES |  | REQUIRED EVENT DOCUMENTS
please link your documents here that require review
PLANNING | Select event date(s) | 0 | <insert name> | 20 | -140 | Not Started |  |  |  | DOCUMENT NAME | URL LINK |  | AUTHOR
| Select venue | 0 | <insert name> | 20 | -140 | Not Started |  |  | 1 | EA approved waiver and Release of Liability | https://www.equestrian.org.au/forms
| Prepare budget | 0 | <insert name> | 20 | -140 | Not Started |  |  | 2 | Contact list
| Book judges | 0 | <insert name> | 19 | -133 | Not Started | Min. 2 EA accredited para dressage judges |  | 3 | Event Management Plan
| Book vet | 0 | <insert name> | 19 | -133 | Not Started |  |  | 4 | Risk Management Plan
| Book farrier | 0 | <insert name> | 19 | -133 | Not Started |  |  | 5 | Rider's Guide
| Book medical team | 0 | <insert name> | 19 | -133 | Not Started |  |  | 6 | Venue Site Plan
| Organise payment agreements for judges | 0 | <insert name> | 18 | -126 | Not Started |  |  | 7 | Volunteer register
| Book accommodation for judges | 0 | <insert name> | 18 | -126 | Not Started |  |  | 8 | Official scratching form
| Sanctioning Application submitted | 0 | <insert name> | 12 | -84 | Not Started |  |  | 9 | Payment form for officials
| Complete Event Sanctioning Agreement | 0 | <insert name> | 12 | -84 | Not Started |  |  | 10 | Dietary requirements form for officials
| Set up event registrations | 0 | <insert name> | 12 | -84 | Not Started | Para dressage tests available |  | 11 | Stable allocations
| Book food vans | 0 | <insert name> | 11 | -77 | Not Started |  |  | 12 | Phone contact list
| Book coffee van | 0 | <insert name> | 11 | -77 | Not Started |  |  | 13
| Organise feed | 0 | <insert name> | 11 | -77 | Not Started |  |  | OTHER EVENT DOCUMENTS
| Book stewards | 0 | <insert name> | 10 | -70 | Not Started | Min. 1 Para Equestrian Steward
| Organise volunteers | 0 | <insert name> | 10 | -70 | Not Started
[10 empty] | DOCUMENT NAME |  |  | AUTHOR
[9 empty] | 1 | Club Insurance Policy
| Get dietary requirements for staff & volunteers | 0 | <insert name> | 2 | -14 | Not Started |  |  | 2 | EA Master List | https://www.equestrian.org.au/content/para-equestrian-classification |  | Equestrian Australia
PROMOTION | Create 'Event' on club's Facebook Page | 0 | <insert name> | 12 | -84 | Not Started |  |  | 3 | Report a Safety Incident |  |  | Equestrian Australia
| Email club membership an entry link | 0 | <insert name> | 12 | -84 | Not Started |  |  | 4 | Doping control requirements | https://www.equestrian.org.au/event-organisers |  | Sport Intergrity Australia
| Promote on club's website | 0 | <insert name> | 12 | -84 | Not Started |  |  | 5 | Compensating Aids list | https://inside.fei.org/fei/disc/para-dressage/classification/documentation |  | FEI
| Post on club's social media accounts | 0 | <insert name> | 12 | -84 | Not Started | regular updates |  | 6 | EA Rules | https://www.equestrian.org.au/rules |  | Equestrian Australia
[9 empty] | 7 | FEI Para Dressage Rules | https://inside.fei.org/fei/disc/para-dressage/rules |  | FEI
[9 empty] | 8 | EA Para Dressage Tests |  |  | Equestrian Australia
PRE-EVENT | Send Officials Information Pack | 0 | <insert name> | 1 | -7 | Not Started | See list |  | 9 | FEI Para Dressage Tests | https://inside.fei.org/fei/your-role/organisers/p-e-dressage/tests |  | FEI
| Provide judges with draw list, timetable and judging positions | 0 | <insert name> | 1 | -7 | Not Started |  |  | 10
| Send rider pack to riders | 0 | <insert name> | 2 | -14 | Not Started | See list |  | SUPPLIER - EVENT SERVICES |  | NAME | EMAIL | CONTACT PHONE
| Venue Facilities Checklist done | 0 | <insert name> | 2 | -14 | Not Started
| Arena set up to change from 60 m x 20m to 40 m x 20m | 0 | <insert name> | 1 | -7 | Not Started |  |  | 1 | Venue
| Notify scorers of updated draw changes | 0 | <insert name> | 0 | -1 | Not Started | check daily |  | 2 | First Aid Provider
| Notify commentator of updated draw changes | 0 | <insert name> | 0 | -1 | Not Started | check daily |  | 3 | Results System
| Send officials updated draw list | 0 | <insert name> | 0 | -1 | Not Started |  |  | 4 | Food provider
| Notify competitors and spectators of any changes | 0 | <insert name> | 0 | -1 | Not Started |  |  | 5 | Coffee van
| Designated warm up area set up | 0 | <insert name> | 1 | -7 | Not Started | Separate area for para athletes if possible |  | 6 | Vet
| Set up check in area | 0 | <insert name> | 1 | -7 | Not Started |  |  | 7 | Farrier
| Provide offical scratching form for athletes/owners and vet | 0 | <insert name> | 0 | 0 | Not Started |  |  | 8 | Feed supply
9
POST-EVENT | Set up accessible presentation area | 0 | <insert name> | 1 | -7 | Not Started |  |  | 10
| Publish results | 0 | <insert name> | 0 | 0 | Not Started |  |  | SUPPLIER - LOCAL SERVICES |  | NAME | EMAIL | CONTACT PHONE
| Reconcile expenses | 0 | <insert name> | -1 | 1900-01-06 | Not Started |  |  | 1 | Local Hospital
| Conduct rider survey | 0 | <insert name> | -1 | 1900-01-06 | Not Started |  |  | 2 | Ambulance Service
| Complete Event report | 0 | <insert name> | -2 | 1900-01-13 | Not Started |  |  | 3 | Police
| Complete Incident log form | 0 | <insert name> | -2 | 1900-01-13 | Not Started |  |  | 4
| Event review | 0 | <insert name> | -2 | 1900-01-13 | Not Started |  |  | 5
INFORMATION PACKS
[11 empty] | Rider's Guide | All Officials | Others
[9 empty] | 1 | Site plan | Yes | Yes
REQUIRED DOCUMENTS | [8 empty] | 2 | Timetable | Yes | Yes
| Event Management Plan | 0 | <insert name> | 12 | -84 | Not Started |  |  | 3 | Draw list | Yes | Yes
| Risk Management Plan | 0 | <insert name> | 12 | -84 | Not Started |  |  | 4 | Judging Positions | No | No | Judges
| Venue plan | 0 | <insert name> | 12 | -84 | Not Started |  |  | 5 | Judges timetable/tests | No | No | Judges
| Event schedule | 0 | <insert name> | 4 | -28 | Not Started |  |  | 6 | Scratching form | No | No | Athletes, owners, vet as required
| Stable allocation | 0 | <insert name> | 3 | -21 | Not Started |  |  | 7 | Payment claim form | No | No | As applicable
| Rider Guide | 0 | <insert name> | 3 | -21 | Not Started |  |  | 8 | Steward's phone contacts, stable allocations, current compensating aids list, current EA Para Dressage Rules | No | No | Chief Judge and Chief Steward
| Timetable | 0 | <insert name> | 3 | -21 | Not Started
| Draw list | 0 | <insert name> | 3 | -21 | Not Started
| Horse inspection list | 0 | <insert name> | 2 | -14 | Not Started
[10 empty] | All officials includes: | Judges
Stewards
Scorers
Commentator(s)
Vet
Classifiers (if applicable)
Formulas:
DEADLINE = C3-([WEEKS PRIOR]*7)
DEADLINE = C3-([WEEKS PRIOR]*7)-1

## 3. Venue Facilities
Category | Item | Applicable | Listed in Event Information | Comment | Resources
PARKING | Parking is level and easily accessible
Designated parking area for people with a disability close to the competition area
Distance, terrain and path surfaces from float parking to any area where events are held
Set down and unloading areas available
Are there boom gates and/or entry gates?
BATHROOMS | Accessible toilets |  |  |  | https://scia.org.au/resource-hub/accessible-toilets/
Terrain and surface to bathrooms accessible
Location of bathrooms in relation to parking and facilities
Bathroom doors open in which direction (e.g. if inwards, do they allow wheelchair access?)
Facilities in the bathroom (rail, seating etc.)
Accessible change areas and shower facilities
Terrain and surface to change areas and showers accessible
GROUNDS | What is road and path surface made from? (tarmac, gravel, sand, grass)
Day yards available?
Ramps or mounting blocks available?
Stairs – especially note if some areas are accessible via the stairs
Entrances and doorways wide enough leading to key areas, i.e. riders’ retreat
Access to event office
Utilities at a suitable height i.e. water, power, registration desk
Power available for day parking
Running water near day parking
Presentation area is accessible
RIDER FACILITIES | Lunging facilities and accessibility of terrain to round yard
Is the venue open for riding before the event?
Arena surface grass, sand, synthetic?
Allocated warm up/familiarisation time for para athletes
Allocated warm up area for exclusive use of athletes with a vision impairment
Results displayed in accessible location
ASSISTANCE ANIMALS | Fenced areas
Leash rules
Non-assistant animals permitted?
SPECTATORS | Is arena viewing suitable from a wheelchair?
Weather protection available
Seating and tables
Designated parking area for people with a disability close to competition area
STABLES | Stables (well-lit, tidy aisles with wide enough space for pram/wheelchair/working frame to pass someone)
Power, running water available and close by
Stables available for stallions
Is bedding available at the venue?
ADDITIONAL EQUIPMENT | The short side of an arena at standard height or a pole to mark the end of the 20 m x 40 m arena
Portable standard letters
Large letters with contrast lettering for Vision Impaired athletes
Spray cans or tape, clips – something to mark the arena letters
Letter covers (if required)
60 m measuring tape
20 m x 40 m and 20 m x 60 m diagrams with measurements
Bell loud enough for athletes with a hearing impairment
Stop watch for judge at C

## Lists
Status
Complete | Yes
In Progress | No
Road Block | N/A
Not Started